## Product Backlog
Planned Sprint | Actual Sprint | Z-ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | Z-4-5 | As a developer, set up the project environment and integrate Groq API | MUST HAVE | Groq | Aman Kumar | 4- Completed
S1 | S1 | Z-4-5 | As a developer, connect to Database and store compliance data in vector form | MUST HAVE | Database | Aman Kumar | 4- Completed
S2 | S2 | Z-4-5 | As a user, upload a contract and get GDPR/DPDPA compliance analysis | MUST HAVE | GDPR/DPDPA | Aman Kumar | 4- Completed
S2 | S2 | Z-4-5 | As a developer, used FAISS is a vector database dependency used to perform fast similarity search on policy embeddings project. | MUST HAVE | Vector Database FAISS | Aman Kumar | 4- Completed
S3 | S3 | Z-4-5 | As a user, received updated contract with no regulatory risk | MUST HAVE | No Dependency | Aman Kumar | 4- Completed
S3 | S3 | Z-4-5 | As a developer, update contracts when new regulatory amendments are released | SHOULD HAVE | No Dependency | Aman Kumar | 4- Completed
S4 | S4 | Z-4-5 | As a developer, automate alert sending via SMTP when a contract is revised to Mail | SHOULD HAVE | SMTP setup | Aman Kumar | 4- Completed
S4 | S4 | Z-4-5 | As a system, I setup a chatbot for each contracts | SHOULD HAVE | Groq LLM APIs | Aman Kumar | 4- Completed
S4 | S4 | Z-4-5 | As a user, I received the revised contract with changes details | MUST HAVE | No Dependency | Aman Kumar | 4- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
Z-ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 81 | 17 | 16 | 14 | 15 | 13 | 9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Z-4-5 | T1-01 | Set up Python virtual environment and install dependencies | 16-Oct-25 | 17-Oct-25 | Dhiraj Suresh Patil | Build | 4- Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Z-4-5 | T1-02 | Integrate Groq API and test LLM response | 18-Oct-25 | 20-Oct-25 | Dhiraj Suresh Patil | Coding | 4- Completed | 3 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Z-4-5 | T1-03 | Set up connection and test connectivity between Groq API | 21-Oct-25 | 31-Oct-25 | Dhiraj Suresh Patil | Integration Test | 4- Completed | 9 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Z-4-5 | T1-04 | Create vector embedding pipeline using LangChain | 1-Nov-25 | 4-Nov-25 | Dhiraj Suresh Patil | Coding | 4- Completed | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Z-4-5 | T2-01 | Upload GDPR and DPDPA Regulatories | 5-Nov-25 | 6-Nov-25 | Dhiraj Suresh Patil | Others | 4- Completed | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Z-4-5 | T2-02 | Perform comprehensive compliance analysis on user contract | 7-Nov-25 | 9-Nov-25 | Dhiraj Suresh Patil | Others | 4- Completed | 10 | 1 | 2 | 1 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Z-4-5 | T2-03 | Update contract if needed updation | 10-Nov-25 | 10-Nov-25 | Dhiraj Suresh Patil | coding | 4- Completed | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Z-4-5 | T2-04 | Display interactive charts based on Analysis | 11-Nov-25 | 12-Nov-25 | Dhiraj Suresh Patil | Analysis | 4- Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Z-4-5 | T3-01 | Track latest regulatory updates | 13-Nov-25 | 19-Nov-25 | Dhiraj Suresh Patil | Coding | 4- Completed | 3 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Z-4-5 | T3-02 | Perform risk assessment on each contract based on regulatory updates | 20-Nov-25 | 21-Nov-25 | Dhiraj Suresh Patil | Coding | 4- Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Z-4-5 | T3-03 | Update contract if needed based on new regulatory updates | 22-Nov-25 | 26-Nov-25 | Dhiraj Suresh Patil | Others | 4- Completed | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Z-4-5 | T4-01 | Integrate SMTP to send alert to owner regarding contract revision | 27-Nov-25 | 5-Dec-25 | Dhiraj Suresh Patil | Coding | 4- Completed | 10 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Z-4-5 | T4-02 | Design ChatBot conversation flow for contract Q/A | 6-Dec-25 | 10-Dec-25 | Dhiraj Suresh Patil | Coding | 4- Completed | 10 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 3 | Lack of Clarity on project requirements | Conduct detail discussion with Mentor
Sprint 1 | Day 6 | Lack of Clarity on project workflow | Conduct detail discussion with Mentor
Sprint 2 | Day 12 | Confusion about analysis report generation | Conduct detail discussion with Mentor
Sprint 2 | Day 20 | Confusion about contract updation | Conduct detail discussion with Mentor
Sprint 3 | Day 25 | Difficulty in regulatory updates tracking | Conduct detail discussion with Mentor
Sprint 3 | Day 30 | Confusion about contract revision | Conduct detail discussion with Mentor
Sprint 4 | Day 35 | Difficulty in SMTP integration | Conduct detail discussion with Mentor
Sprint 4 | Day 42 | Difficulty in chatbot integration | Conduct detail discussion with Mentor

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 16-Oct-25 | 4-Nov-25 | MACERNESTANTONY D | Implementing comprehensive error handling for API failures | Skipping integration tests before committing | Daily code reviews and pair programming sessions | Established automated API monitoring with alert thresholds
2 | 2 | 5-Nov-25 | 12-Nov-25 | MACERNESTANTONY D | Conducting pre-analysis validation of contract formats | Manual vector embedding verification processes | Maintaining detailed schema documentation with version control | Implemented automated embedding quality validation pipeline
3 | 3 | 13-Nov-25 | 26-Nov-25 | MACERNESTANTONY D | Implementing regulatory webhook subscriptions for real-time updates | Assuming static compliance rules without version tracking | Maintaining changelog of all regulatory amendments | Created automated version comparison and impact assessment tool
4 | 4 | 27-Nov-25 | 10-Dec-25 | MACERNESTANTONY D | Implementing multi-channel notification fallback strategies | Hardcoding email templates without localization | Documenting all conversational flows and edge cases | Developed A/B testing framework for ChatBot prompt optimization